## Overview
Item | Description
Product Name | GymTrack (GymTrack Lite + Member Hub + SuperAdmin Portal)
Product Vision / Purpose | To build a seamless, all-in-one ecosystem connecting gym owners, trainers, and members. GymTrack simplifies gym operations, enhances member experience, and provides data-driven insights for efficient growth.
Business Goals / Key Success Factors | • Streamline gym management (memberships, check-ins, analytics, billing) • Improve member engagement (workouts, messaging, progress tracking) • Deliver real-time insights to increase retention and revenue • Provide a modern, mobile-first experience • Ensure reliable, scalable architecture using Next.js + Supabase
Primary Stakeholders | • Gym Owners & Staff (GymTrack Lite) • Gym Members (Member Hub) • Platform Admins (SuperAdmin Portal) • Trainers (benefit from member progress insights)

## Release Plan
Release | Target Date | Key Features (Epic Names) | Dependencies | Demo Status
v0.1 | 01-Sep | Authentication, Member Lookup, Dashboard MVP | None | Completed
v0.2 | 08-Sep | Profile Card, Membership Status Badge, QR Code Generator | Member DB schema finalization | Completed
v0.3 | 15-Sep | Workout Logging, Workout History, Weight Tracking Charts | Chart library integration | Completed
v0.4 | 22-Sep | Personal Records (1RM), Workout Overview Dashboard | Workout logs processing | Completed
v0.5 | 29-Sep | Gym Announcements, Realtime Messaging | Supabase Realtime setup | Completed
v1.0 | 06-Oct | Membership Renewal (UPI), Check-in History (Charts) | UPI payment integration | Completed
v1.1 | 13-Oct | AI Fitness Assistant Chatbot, Workout Planner | Genkit + Gemini API | Completed
v1.2 | 2025-11-17 | Gamification & Streaks | None | Completed
v1.4 | 2025-11-17 | Dark Mode + Dashboard Personalization | None | Completed
v1.6 | 2025-11-25 | Push Notifications & Reminders | Notification service setup | Ongoing
v1.3 | 2025-11-17 | Class Booking System | GymTrack Lite sync | Ongoing
v1.5 | 2025-12-10 | Nutrition Logging & AI Meal Planner | Gemini API | Planned

## Backlog
Epic ID | Epic Title | User Story ID | User Story / Requirement | Technical Requirements | Priority (MoSCoW) | Story Points | Status | Owner | Test Case (Tasks) | Test Owner
E1 | User Authentication | US1 | As a user, I want to sign in with email + Member ID so that I can securely access the Member Hub. | Login screen, input validation, credential verification API | Must Have | 8 | Completed | Backend Dev | Test login flow, invalid login, member lookup | QA
E2 | Dashboard | US4 | As a user, I want a personal dashboard with my membership status so that I can see key info quickly. | Dashboard UI, membership expiry logic, badge color rendering | Must Have | 5 | Completed | Frontend Dev | Verify status badge, expiry dates | QA
| Dashboard | US5 | As a user, I want to see my gym info and quick links to all features. | Gym info API, UI cards | Should Have | 3 | Completed | Frontend Dev | UI component tests | QA
E | Workout Tracking | US6 | As a user, I want to log workouts with exercises, sets, reps, and weight. | Workout form UI, dynamic exercise list, DB table for workouts | Must Have | 13 | Completed | Frontend + Backend | Test multi‑exercise entry, validation | QA
| Workout Tracking | US7 | As a user, I want to view my workout history in an expandable list. | Workout history query, accordion UI | Must Have | 8 | Completed | Frontend Dev | Test data retrieval, UI expand/collapse | QA
| Workout Tracking | US8 | As a user, I want to track my weight history and see a trend chart. | Chart library integration, weight log API | Should Have | 5 | Completed | Frontend Dev | Chart rendering tests, data accuracy | QA
E4 | Strength Records | US9 | As a user, I want to see my personal records calculated automatically. | 1RM formula engine, data aggregation | Should Have | 8 | Completed | Backend Dev | 1RM calculation test cases | QA
| Strength Records | US10 | As a user, I want an overview of total workouts, weight trends, and top lift. | Metric aggregation, dashboard UI cards | Could Have | 3 | Completed | Frontend Dev | Metric validation tests | QA
E5 | Messaging | US11 | As a user, I want to chat with gym admin in real-time. | Realtime DB channels, message sync, UI chat bubbles | Must Have | 13 | Completed | Fullstack | Realtime sync test, send/receive tests | QA
E6 | Announcements | US12 | As a user, I want to see latest announcements from my gym. | Announcements API, sorted query | Should Have | 3 | Completed | Frontend Dev | Content rendering test | QA
E7 | Payments & Membership | US13 | As a user, I want to renew/purchase a plan via UPI QR. | UPI QR generation, amount validation | Must Have | 13 | Completed | Backend Dev | UPI QR test, payment link tests | QA
| Payments & Membership | US14 | As a user, I want to view available membership plans. | Plans API, price formatting | Must Have | 5 | Completed | Frontend Dev | Test plan loading and display | QA
E8 | Check‑in History | US15 | As a user, I want to see my past check-ins grouped by month. | Grouping logic, history API, month filter | Should Have | 5 | Completed | Backend + Frontend | Validate grouping & chart data | QA
| Check‑in History | US16 | As a user, I want a chart showing my monthly visit frequency. | Chart integration, monthly stats | Could Have | 3 | Completed | Frontend Dev | Chart accuracy tests | QA
E9 | AI Assistant | US17 | As a user, I want to chat with an AI fitness assistant for guidance. | Genkit AI API integration, context memory | Should Have | 8 | Completed | Backend Dev | AI prompt tests, rate limit tests | QA
| AI Assistant | US18 | As a user, I want an AI-generated workout plan based on my level. | AI plan generator, form UI | Could Have | 8 | Completed | Backend + Frontend | Validate plan accuracy & formatting | QA
E10 | Gamification | US19 | As a user, I want streak tracking so I stay motivated. | Streak calculation engine, daily sync | Should Have | 5 | Yet to Plan | Backend Dev | Streak calculation tests | QA
| Gamification | US20 | As a user, I want achievement badges. | Badge rules, unlock logic | Could Have | 3 | Yet to Plan | Frontend + Backend | Badge unlock test cases | QA
E12 | Nutrition | US22 | As a user, I want to log meals and track calories. | Nutrition DB, meal entry UI | Could Have | 8 | Yet to Plan | Frontend + Backend | Test macros & totals | QA
E13 | Notifications | US23 | As a user, I want push reminders for workouts and membership renewal. | Notification service, scheduler | Should Have | 8 | Yet to Plan | Backend Dev | Notification delivery tests | QA
| User Authentication | US2 | As a user, I want OTP verification when changing my email so that my account stays secure. | OTP generation, email service integration | Should Have | 5 | Completed | Backend Dev | Test OTP send, validate OTP, expire OTP | QA
| User Authentication | US3 | As a user, I want to update my profile details such as name, age, phone. | Profile update API, validation rules | Must Have | 3 | Completed | Backend Dev | Test update API, invalid fields | QA